INTERNAL — TEAM EXECUTION PLAN

BIMModeller Revit Plugin

Week-by-week build plan. Core scope vs add-on scope. For the engineering team.

| AUDIENCE | Engineering team — internal only |
| --- | --- |
| PROJECT LEAD | Kumaravel |
| DATE | May 2026 |
| VERSION | v1.4 — zero-cost staging + 2-person parallel (supersedes v1.3) |
| DURATION | 10-12 calendar weeks from kickoff to GA |
| CORE SCOPE | Separate window UI + OAuth + subscription gating + REST API + admin dashboard + per-user telemetry + Revit 2027 QA + 30-day bug-fix |
| ADD-ON SCOPE | Beta, multi-version QA, support hand-off, launch marketing, personas, extended support — only execute on signed change order |
| KEY CHANGE | v1.3 → v1.4: (1) staging Magento hosted free via local Docker + Cloudflare Tunnel, $0/month. (2) Engineering work split into two parallel tracks — Backend dev owns staging + BIMM_Connect module; Plugin dev owns the Revit plugin. Tracks sync at the API contract. |

# 1.  Project at a glance

## 1.1  Primary goal

Deliver a working Revit plugin matching the visual pattern of the Bim.com Design App (separate floating window with sidebar nav) — using BIMModeller's 3,874-family catalog — with OAuth authentication via bimmodeller.com and server-side subscription enforcement. Server-side delivered as a Magento 2 module (BIMM_Connect) hosted free via local Docker + Cloudflare Tunnel. Two engineers work in parallel — one on the Magento staging + module, one on the Revit plugin — meeting only at the REST API contract. Provide 30 days of bug-fix support after GA. Nothing else is core scope.

## 1.2  Core scope (what we are paid to deliver)

- BIMModeller Revit plugin (signed MSI, auto-update) — opens as separate WPF Window with sidebar (Projects · Discover · Libraries).

- Libraries tab placeholder ("Coming soon" — Tutorial 2 functionality NOT in scope).

- BIMM_Connect Magento 2 module: REST endpoints under /rest/V1/bimm/* + OAuth (Magento 2 native + PKCE wrapper) + subscription enforcement on /family/{id}/download using Magento customer groups.

- OAuth sign-in flow: Authorization Code + PKCE via system browser; localhost callback; DPAPI-encrypted token storage.

- Admin insights dashboard with PER-USER telemetry (KPIs, top loads, demand gaps, user-level breakdowns).

- Functional + performance QA on Revit 2027.

- User guide, admin guide, knowledge transfer session.

- 30-day bug-fix support post-GA.

## 1.3  Add-on scope (only if client signs a change order)

The items below are NOT part of the core engagement. If the client wants any of them, the project lead negotiates the scope and price, gets a signed change order, then the team executes. Do not execute speculatively.

- Beta architect programme (recruitment, onboarding, feedback collection — Wk 6+).

- Multi-Revit-version QA on 2024, 2025, 2026 (requires client to provide Revit licenses or VMs).

- Customer support hand-off runbook + training session.

- Launch marketing assets (email, banner, blog, video, social).

- Test architect personas (research deliverable).

- Extended bug-fix support beyond 30 days.

- v1.1, v1.2, v2.0 future enhancements.

## 1.4  Success criteria (concrete, testable)

- On clean Windows + Revit 2027: install MSI → restart Revit → click BIMModeller tab → window opens → Sign in via browser → return to window → search → load → see family in 3D + plan within 120 seconds end-to-end.

- OAuth round-trip works on Chrome, Edge, Firefox. Token persists across Revit restarts.

- Subscription tier limits enforced: a Lite user hitting their cap gets a 402 + upgrade prompt; a Pro user has no limit.

- All 3,874 families browseable and loadable; Load latency < 3 seconds.

- Signed MSI published at bimmodeller.com/revit-plugin; auto-update endpoint returns 200.

- Telemetry events appear in admin dashboard within 30 seconds of emission.

- Zero P0 and zero P1 bugs open at GA.

## 1.5  Explicitly out of scope

- 3D preview pane (would need glTF pipeline).

- Functional Libraries tab — saved family library, team sharing (Tutorial 2 scope).

- LCA / CO2 (Tutorial 3).

- AI workflows (Phase 5 separate roadmap).

- Non-Revit hosts; macOS; localisation beyond English.

## 1.6  Two parallel tracks

Engineering work is split into two independent tracks that meet only at the REST API contract (Architecture §11). Each track has one full-time engineer who can develop without waiting on the other after Week 2.

| Track | Scope |
| --- | --- |
| Track A — Staging & Magento module | Owns the local Docker Magento + Cloudflare Tunnel staging URL. Builds the BIMM_Connect Magento 2 module: REST endpoints, OAuth wrapper, subscription enforcement, telemetry ingestion, admin dashboard wiring. Imports 3,874-product seed data. Handles cutover to real bimmodeller.com when access arrives. |
| Track B — Revit plugin | Owns the Revit add-in: C# solution (Core, UI, App projects), WPF separate window, MVVM viewmodels, REST client, OAuth client (PKCE + DPAPI), Revit API integration (LoadFamily, Replace, multi-view), installer + auto-update, QA on Revit 2027. |

Both tracks start Day 1. The only hard sync point is the API contract sign-off at the end of Week 2 — after that, Track A delivers against the spec, Track B consumes the spec, and they meet at phase-gate reviews.

## 1.7  Sync points and contract discipline

- Daily 15-minute standup — both tracks attend; covers blockers only.

- Weekly Thursday demo (30 min) — each track shows progress; helps catch contract drift early.

- API contract changes require a PR with sign-off from BOTH tracks. No unilateral changes to §11 of the architecture doc.

- Shared Slack channel #api-contract used only for spec discussions; everything written, not verbal.

- Phase gates (end of weeks 2, 7, 9, 11) are joint reviews — both tracks must be green to pass.

# 2.  Team and roles

| Role | Allocation (core) | Responsibility |
| --- | --- | --- |
| Track B — Plugin dev (Senior Revit / C#) | 100% × 11 wks | Plugin architecture, separate WPF Window with sidebar nav, Revit API integration, multi-view orchestration, OAuth client (PKCE + DPAPI), 402 upgrade UX, installer + auto-update |
| Track A — Backend dev (Magento 2 + staging owner) | 100% × 11 wks | Local Docker Magento + Cloudflare Tunnel staging. BIMM_Connect Magento module: REST controllers, PKCE wrapper around Magento native OAuth, customer-group subscription enforcement, telemetry, admin dashboard backend. Seed-data import. Cutover to bimmodeller.com. |
| UI / UX designer | 50% × 6 wks | Separate-window layout, sidebar nav, sign-in screen, 402 upgrade-prompt UX, brand application |
| QA engineer | 50% × 5 wks | Functional + performance + OAuth + subscription enforcement + regression on Revit 2027. Multi-version testing is an add-on. |
| Project lead (Kumaravel) | 25% × 11 wks | BIMModeller liaison, status, gates, risk, scope decisions, change-order negotiation if add-ons sold |

# 3.  Week-by-week schedule

Project total duration: 7-9 calendar weeks. Each row is a calendar week. Phase gates at the end of weeks 2, 5, 7, and 9.

| Wk | Phase / Theme | Deliverables (CORE only) | Primary owner(s) |
| --- | --- | --- | --- |
| 1 | P1 · Kickoff | Receive BIMModeller items; [Track A] stand up Magento Docker + Cloudflare Tunnel — public staging URL live; create 3 repos; OAuth flow + window-shell wireframes drafted; CDN/storage decided; cert ordered; project clock starts | Lead, Designer, Track A, Track B |
| 2 | P1 · Architecture | API contract signed off (incl. OAuth + /me); bimm-connect skeleton on staging (read-only); plugin shell launches separate WPF Window from ribbon; CI green on Revit 2027. GATE P1. | Plugin, Backend |
| 3 | P2 · Window shell | WPF Window with sidebar (Projects · Discover · Libraries-placeholder); top filter bar; brand applied; mock data wired | Plugin, Designer |
| 4 | P2 · Categories + Search | 20+ categories in Discover; category drill-down; search + filter chips; product detail page renders; anonymous mode (no auth yet) | Plugin, Backend |
| 5 | P2 · Load + Replace | Live REST API; Load command for 100 families; multi-view orchestration after Load; Replace command | Plugin, Backend |
| 6 | P2 · Polish + scale | All 500 priority families loadable; error states; loading indicators; window state persistence; bugfix sprint #1 | Plugin, QA |
| 7 | P2 · MVP gate | All 3,874 families loadable; UI polish complete; admin dashboard skeleton with anonymous events; internal regression green. GATE P2. | All |
| 8 | P3 · OAuth | Auth Code + PKCE flow live: Sign in → browser → bimmodeller.com → callback → token captured + DPAPI encrypted; /me endpoint; per-user telemetry replaces anonymous | Plugin, Backend |
| 9 | P3 · Subscription gating | Subscription tier rules implemented in WP admin; /family/{id}/download enforces tier; 402 upgrade prompt in plugin; admin dashboard shows per-user breakdown. GATE P3. | Backend, Plugin |
| 10 | P4 · GA prep | Signed MSI; auto-update channel live; landing page deployed on bimmodeller.com; documentation written (user guide, admin guide, FAQ); cert integrated; cosmetic polish | All |
| 11 | P4 · GA + launch | Public release; first customers signing in + loading; telemetry confirms 100+ installs; bug triage queue handed off. GATE P4 (final). | All |

## 3.1  Note on what is NOT done by default

- Beta architect onboarding (Wk 6) — only if Beta add-on sold. Otherwise QA does internal regression only.

- Multi-version regression — only on Revit 2027. Other versions are use-at-own-risk unless Multi-Version QA add-on sold.

- Launch email / banner / blog — drafts are NOT produced unless Launch Marketing add-on sold.

- Support runbook — NOT written unless Support Hand-off add-on sold.

# 4.  Engineering tasks per phase

## 4.1  Phase 1 — Kickoff & setup (Wk 1-2)

- Receive BIMModeller kickoff items per Client Handover §3.1 + §3.2; confirm in writing; project clock starts.

- [Track A] Confirm Magento version (target: 2.4.7 Open Source) — client confirmation not required since we host our own staging.

- [Track A] Stand up local Magento dev environment via Docker (markoshust/magento-docker base) per Architecture §22.

- [Track A] Set up Cloudflare Tunnel (free) per Architecture §22.12 — public URL like https://bimm-dev.{domain}.com is live by end of Day 2.

- [Both tracks] Create three repos: bimmodeller-revit-plugin (Track B), bimm-connect Magento module (Track A, composer.json type magento2-module), bimm-admin-dashboard (Track A).

- [Track B] Plugin: bootstrap C# solution (Core, UI, App) with multi-target .csproj (net48 + net8.0-windows + net10.0-windows); CI green on Revit 2027.

- [Track A] Magento module: registration.php, etc/module.xml (depends on Magento_Customer, Magento_Catalog, Magento_Webapi, Magento_Integration), etc/db_schema.xml, etc/webapi.xml; /rest/V1/bimm/health returns 200 on staging Magento (the Cloudflare-tunnelled URL).

- Designer: wireframes for all 7 screens; review with project lead.

- Order code-signing certificate from CA (5 business days budget).

- Register OAuth client in dev Magento admin: Magento native OAuth has built-in client management; we add PKCE field via our module.

- Decide CDN/storage; provision bucket; set retention + cache headers.

- ADR for: auth-agnostic design, telemetry schema, error envelope.

- Phase 1 gate: ADR signed; staging operational; CI green; brand assets received.

## 4.2  Phase 2 — Core MVP (Wk 3-7)

- Plugin: convert from DockablePane to standalone WPF Window class; window lifecycle (open from ribbon, close X, remember size/position).

- Plugin: sidebar nav component (Projects · Discover · Libraries-placeholder); top filter bar (File types + Categories dropdowns + Search).

- Plugin: 20+ categories grid in Discover; category drill-down; product card list; product detail page.

- Plugin: Search service with server-side full-text search; filter chips (manufacturer / compliance / mounting).

- Plugin: Load command — Document.LoadFamily + Transaction + ElementPlacement at cursor.

- Plugin: Replace command (in-place swap preserving location + rotation).

- Plugin: multi-view orchestration ({3D} + Level plan side-by-side, zoom-to-fit).

- Plugin: anonymous telemetry events POST to /wp-json/bimm/v1/events with per-install ID (auth added in Phase 3).

- WP connector: /products (paginated), /categories, /search, /family/:id/download (signed CDN URL — no auth gate yet).

- WP connector: /events ingestion with rate limiting + schema validation.

- Designer: final visual design as Figma frames; sign-in screen mockup (for Phase 3 use).

- Admin dashboard skeleton — KPI cards from /events aggregate (anonymous in P2; per-customer in P3); mounted into Magento admin via Controller/Adminhtml/Insights/Index.php + view/adminhtml layout XML.

- QA: integration test plan; Revit 2027 regression suite running.

- Phase 2 gate (end of Wk 7): all 3,874 families loadable; UI polish complete; internal regression green; demo recorded.

## 4.3  Phase 3 — Auth + Subscription gating (Wk 8-9)

- Plugin: Sign-in screen UI (shown when no valid token); Sign in button opens system browser to OAuth URL with PKCE challenge.

- Plugin: localhost HTTP listener on a high port (registered as redirect URI in bimmodeller.com OAuth client config); captures authorization code; exchanges for token.

- Plugin: token storage via Windows DPAPI; access token + refresh token; silent refresh on expiry.

- Plugin: bearer-token injection on every API call; 401 handling (refresh and retry once, then prompt re-sign-in).

- Plugin: Sign-out (revokes token on server, clears local DPAPI store, resets UI).

- Plugin: 402 Payment Required handler — render upgrade-prompt modal with deep link to bimmodeller.com upgrade page.

- Magento module: PKCE wrapper layered on Magento 2 native OAuth — /rest/V1/bimm/oauth/authorize, /oauth/token, /oauth/refresh, /oauth/revoke.

- Magento module: native Magento customer_entity as identity source — no separate IdP needed.

- Magento module: /rest/V1/bimm/me returns customer + group (tier) + remaining quota (from bimm_quota_used_this_month customer attribute).

- Magento module: subscription enforcement on /family/{id}/download — server-side check using customer.group_id → tier config; returns 200 + signed URL OR 402 + upgrade message.

- Magento admin: tier configuration UI (Stores → Configuration → BIMModeller → Tiers) declared in etc/adminhtml/system.xml; backed by bimm_subscription_tier_config table.

- Telemetry: events now keyed by user ID (not anonymous); user-level breakdowns surface in admin dashboard.

- Admin dashboard: per-user pages, per-tier breakdowns, conversion funnel (Lite → Essential → Pro).

- QA: end-to-end OAuth on Chrome, Edge, Firefox; expired-token recovery; revoke flow; subscription-limit hit; offline at sign-in.

- [ADD-ON CHECK] If Beta programme add-on sold: onboard 10-15 architects in Wk 8 (after OAuth ships); collect feedback. Otherwise SKIP.

- [ADD-ON CHECK] If Multi-Version QA add-on sold: run regression on Revit 2024/2025/2026. Otherwise SKIP.

- Phase 3 gate (end of Wk 9): full sign-in flow working; subscription tiers enforced; 402 upgrade prompt renders; admin dashboard shows per-user data; 0 P0 bugs.

## 4.4  Phase 4 — Polish + GA (Wk 10-11)

- Installer: WiX MSI build; Squirrel auto-update channel; smoke-test on clean Windows 10 + 11 VMs (signed in + signed out flows both).

- Backend: /version-manifest endpoint.

- Deployment: bimmodeller.com/revit-plugin landing page with download button + "Sign in to start" copy.

- Documentation: user guide (sign-in walkthrough + Load workflow, ~14 pages), admin guide (tier configuration, telemetry dashboard, ~10 pages), FAQ.

- Cosmetic polish: P2/P3 bugs; copy polish; icon refinement; OAuth UX polish.

- Telemetry: end-to-end load test with 100 simulated user events; admin dashboard validated.

- [ADD-ON CHECK] If Support Hand-off add-on sold: write runbook (including OAuth troubleshooting + tier-limit FAQ) + run 90-min training. Otherwise SKIP.

- [ADD-ON CHECK] If Launch Marketing add-on sold: draft email + banner + blog + social. Otherwise SKIP.

- Phase 4 gate (final, end of Wk 11): public download live; first 100 installs telemetry-confirmed; signed users actively loading; project closes.

# 5.  Tools, repositories, infrastructure

| Asset | Detail |
| --- | --- |
| Plugin repo | bimmodeller-revit-plugin (Git, private). C# .NET multi-target (net48, net8.0-windows, net10.0-windows). Solution: BIMModeller.sln (Core, UI, App). |
| Magento module repo | bimm-connect (Git, private). Magento 2 module (composer type magento2-module). PHP 8.1+, PHPStan level 5, Magento Coding Standard. |
| Admin dashboard repo | bimm-admin-dashboard (Git, private). React + TypeScript + Vite. Hosted on bimmodeller.com/admin/plugin-insights. |
| CI/CD | GitHub Actions. Plugin: Revit 2027 build matrix (Multi-Version QA add-on extends to 2024-2026). Magento module: install Magento 2.4 + run PHPStan + PHPUnit + Magento integration tests inside CI. |
| Issue tracker | GitHub Projects per-repo board. Labels: phase-1..4, priority p0..p3, type bug/feat/chore, addon=true if work is conditional on add-on sale. |
| Comms | Slack: #general, #plugin-eng, #wp-eng, #design, #qa, #client-bimmodeller. Daily 15-min standup 09:30 IST. |
| Staging environment (Day 1 → cutover) | Local Docker Magento on Track A engineer's laptop + Cloudflare Tunnel → https://bimm-dev.{domain}.com. ZERO ongoing cost. See Architecture §22.12 for setup. Cutover to client-provided bimmodeller.com staging happens after client grants access. |
| Cloudflare Tunnel | cloudflared CLI on Track A engineer's laptop exposes the local Magento Docker stack at a public HTTPS URL. Free tier sufficient for the project. SSL auto-provisioned by Cloudflare. |
| Code-signing cert | Procured + owned by BIMModeller (legal requirement). Integrated as GitHub Actions secret. We do not store the cert long-term. |
| Installer toolchain | WiX Toolset v4. Squirrel.Windows for auto-update. Artefacts pushed to bimmodeller.com static hosting. |
| OAuth server | Magento 2 native OAuth 2.0 with PKCE wrapper layered by BIMM_Connect. Endpoints under /rest/V1/bimm/oauth/*. Token signing reuses Magento's crypto primitives + JWT for plugin-issued tokens. |
| OAuth client config | Client ID + redirect URI (localhost:PORT/callback) registered in Magento admin via custom CLI bin/magento bimm:oauth:register-client. PKCE required — no client secret needed for desktop apps. |
| Subscription rules storage | Magento customer groups (Lite/Essential/Pro) + custom bimm_subscription_tier_config table. Editable via Magento admin (Stores → Configuration → BIMModeller → Tiers) without redeploy. |
| Telemetry backend | Endpoint: bimmodeller.com/rest/V1/bimm/events. Per-customer keyed (post-Phase-3). Storage: custom MySQL table bimm_event declared in etc/db_schema.xml. Retention: 13 months via Magento cron. |
| Revit licenses for QA | CORE: only Revit 2027 (developer machine). For multi-version testing: client must provide licensed access or VMs. |

# 6.  Dependencies and blockers

| Dependency | Needed by | Mitigation if late |
| --- | --- | --- |
| Magento module install permission on bimmodeller.com (composer require + bin/magento) | Pre-GA (Wk 10) | DEFERRED from Wk 1 to Wk 10 — engineering is unblocked because Track A hosts staging on a free Cloudflare Tunnel. Client permission only needed for production cutover. |
| Staging Magento environment access (client) | Pre-GA (Wk 10) | REMOVED as a blocker — we host our own staging via local Docker + Cloudflare Tunnel from Day 1 (Architecture §22.12). Client access only needed at cutover time (Wk 10). |
| Brand assets | Wk 1 | Placeholder navy/blue/gold theme until real assets arrive; trivial cosmetic swap later. |
| Bulk export / live access to 3,874 .rfa files | Wk 2 | Start with 500-family subset; ingest remainder in batches by Wk 6. |
| OAuth provider decision | Wk 1 | Default to Magento native customer accounts (recommended — already integrated). If alternative chosen, add 3-5 days for IdP-specific integration in Phase 3. |
| Domain for Cloudflare Tunnel (named tunnel) | Wk 1 | Need a domain on Cloudflare for a stable staging URL (~$10/yr if not owned). Acceptable fallback: TryCloudflare with rotating URLs (zero-cost but URL changes per restart). |
| Subscription tier rules (names, limits, prices) | Wk 7 | Phase 3 server-side enforcement is paused until tier rules are provided. Surface in weekly status email if slipping. |
| Code-signing certificate (BIMModeller-owned) | Wk 7 | Order in Wk 1 — 3-day CA lead time leaves 5-week buffer. Pre-identify Sectigo as backup CA. |
| Revit licenses for non-2027 testing | Wk 6 (only if Multi-Version QA add-on sold) | If add-on sold but client cannot provide access: regression matrix shrinks to whichever versions are accessible; flag in writing. |
| MSI hosting URL on bimmodeller.com | Wk 8 | GitHub Releases as fallback if bimmodeller.com hosting decision unresolved (note: URL doesn't carry BIMModeller brand). |

# 7.  Risk register

| Risk | Likelihood | Impact | Owner / mitigation |
| --- | --- | --- | --- |
| BIMModeller delays Section 3 items at kickoff | Medium | High | Project lead — pre-kickoff checklist signed before contract; weekly nudges; SPOC named. |
| Cert procurement delayed > 1 wk | Low | Medium | Project lead — order Wk 1; backup CA pre-identified. |
| Backend dev lacks Magento 2 experience | Medium | Medium | Project lead — confirm backend dev has Magento 2 experience at hiring. If borderline, add 3-5 days ramp-up time in Wk 1. Magento Marketplace Coding Standard + Mark Shust Magento tutorials are the recommended ramp-up. |
| OAuth callback fails (firewall blocks localhost, port collision) | Medium | Medium | Plugin lead — implement port-range fallback (try 47620, 47621, ...); add device-code flow as backup. |
| Subscription tier rules change late in Phase 3 | Low | Low | Backend dev — tier rules in WP admin config, not code. Change is data-only. |
| Client expects multi-version QA in core scope (scope creep) | Medium | Medium | Project lead — Client Handover §7.2 + §8.2 are crystal clear; reinforce at every gate; quote change-order if asked late. |
| Client expects support / marketing / beta in core scope | Medium | Medium | Project lead — these are Section 8 add-ons; refer client back to the handover doc when asked. |
| Revit API differences across 2024-2027 | Medium | Low (core) | Plugin lead — multi-target csproj built from Day 1; only matters if Multi-Version QA add-on sold. |
| Magento module breaks site on bin/magento setup:upgrade | Low | High | Backend dev — develop on staging only; load test before prod deploy; rollback plan written. |
| Telemetry pipeline drops events under load | Low | Low | Backend dev — load test Wk 7 (1000 events/min); rate limiting; client-side retry. |

# 8.  Communication cadence

| Event | When | Format |
| --- | --- | --- |
| Daily standup | Mon-Fri 09:30 IST | 15 min Slack huddle. All eng + design + QA. |
| Weekly status email | Mon 18:00 IST | Project lead → BIMModeller. Shipped / in-flight / blockers / decisions. |
| Fortnightly demo | Wk 2, 4, 6, 8 — Thursday | 30 min recorded. Live demo. SME + leadership invited. |
| Phase-gate review | End of Wk 2, 5, 7, 9 | 60 min. Project lead + BIMModeller decision-maker. Outcome documented. |
| Risk review | Every other Wednesday | 30 min internal. Walk the risk register; reassess. |
| Change-order discussions | As triggered | Project lead only. Any client request that maps to Section 8 add-ons is logged and quoted; team does NOT begin work until change order signed. |

# 9.  Pre-kickoff checklist

Project lead drives this with BIMModeller. Project clock starts only when every line below is checked.

- ☐  Signed proposal received.

- ☐  Tranche 1 invoice issued and paid.

- ☐  Magento module install permission confirmed in writing (composer + bin/magento access); SPOC named.

- ☐  Track A engineer's laptop has Docker Desktop installed.

- ☐  Track A engineer has access to a domain on Cloudflare (for named tunnel) OR is OK with TryCloudflare random URLs.

- ☐  Brand assets received: logo SVG, color palette, typography, plugin icon.

- ☐  SME named, 2-3 hrs/wk availability confirmed.

- ☐  Decision on public-API content scope made.

- ☐  CDN/storage provider chosen; bucket provisioned.

- ☐  Code-signing certificate ordered (BIMModeller-owned).

- ☐  Revit version policy confirmed: Revit 2027 only OR Multi-Version QA add-on signed.

- ☐  OAuth provider chosen (default: Magento native customer accounts via Magento 2 OAuth).

- ☐  Subscription tier rules drafted (names + per-tier load limit) — confirmable by Wk 7.

- ☐  Add-ons signed: which (if any) of §1.3 items are bought; change orders signed.

- ☐  Slack workspace + shared calendar live.

# 10.  References

- Client Handover v1.2 — what BIMModeller sees (companion doc; will be updated to v1.3 Magento if shared with client).

- Architecture, Design & Implementation v1.1 Magento — the authoritative technical reference. Markdown source is the canonical input for Claude Code, Codex, and Antigravity.

- Deep-Dive Analysis v1.2 — 45-page technical reference.

- Interactive prototype — deployed clickable mock; ground truth for UX behaviour.

- POC repository — starting point for the plugin build.